## ST Dashboard
GHD Job Number | ST Reference No. / Purchase Order Number | Project Name | GHD Project Manager | ST Design Manager | Phase | Schedule | Contractual Completion Date | Forecast Completion Date | Current Status | Next Actions
212527 |  | Sydney Trains Darlington | Matthew West
2125740 |  | OTFORD ACCESS WAY UPGRADE PROJECT | Michael Hastings
2126288 |  | Lawrence Hargrave Drive, Thirroul OB - Stage 2 | Tim Wilson
2126373 | PO 4200056952 | Lapstone, Glenbrook & Lithgow SRA & Design | Jason Hellmuth | Prineesh Alphonse | Detailed Design | On track | 2020 (Moving to detailed design variation and then CPS) | 2020 (Moving to detailed design variation and then CPS) | Preparing first draft of heritage reports to inform Options Finalisation meeting / preparing detailed design variation | Finalise detailed design solution, then move to DD phase
2126389 | Purchase order: EC2736 | Beverly Hills Signal Hut & Bardwell Park | Sami Ali Khan | Jason Byrne / Sonia Gupta | AFC |  | Scope of project was only up to AFC phase and did not include Construction services / advice | TBC | In discussion with Sydney Trains for variation to continue works during construction phase. | Sydney Trains and GHD to confirm variation.
2126427 | P.0029917 | Katoomba Substation Embankment Stabilisation | Guillaume de Swardt | Prineesh Alphonse
2126444 | EC6945, 4200058829, 4200059761, 4200111326, | ST MSA MDP - DP4460 - 6 Culverts Upgrade | Matt Presswell | Geoff Wooden | AFC | On track | TBA - pending acceptance of offer for construction phase support on Heathcote. | TBA - pending acceptance of offer for construction phase support on Heathcote. Kembla Grange sites will be probably delivered in next couple of weeks. | Mortdale - scope completed; Coledale - scope completed; Heathcote - CPS offer submitted to ST; KG91.005 - Updated design comments received on 100%, being addressed, updated AFC design being prepared; KG91.860 - AFC deliverables being prepared. Will be delivered this week. Berry - scope completed. | Mortdale - scope completed; Coledale - scope completed; Heathcote - CPS offer submitted to ST; KG91.005 - Updated design comments received on 100%, being addressed, updated AFC design being prepared; KG91.860 - AFC deliverables being prepared. Will be delivered this week. Berry - scope completed.
2126453 |  | Unwins Bridge Rd OB Refurbishment | Tim Wilson
2126473 | P.0027794 | ST MSA MDP - EC8299 - 3 Sydenham Culverts | Matt Presswell | Bhaumik Trivedi | Detailed Design | On track | TBA - pending iterations and review comments from ST. | TBA - pending iterations and review comments from ST. | 4.990km - ST currently cleaning out; 5.240km - 70% DD issued to ST for review; 5.515km - 95% DD issued to ST for review; | Complete next Detailed Design stages
2126491 |  | Canterbury Relocation UGOH Poles | Amit Narsey
2126543 | 4200084067, 4200084070, 4200084072 | ST MSA MDP - Hamilton-Berowra-Wyee OB's | Luke Weatherstone | Sam Widjaja | Concept Design | Behind schedule | 30-06-2018 | 30-08-2019 | Finalising concept options (stage 1) | Respond to ST comments
2126557 | P.0027306 | Austinmer Cutting Downside 68.685km to 68.896km Illawarra | Keith Holden | Bhaumik Trivedi | Options Assessment | Behind schedule | 2018 | 2020 | GHD closed-out 95% Concept Design comments on 7 Jan 2019. | Awaiting agreement between ST and Wollongong City Council (WCC) to install soil nails extending beyond boundary into WCC land.
2126558 | P.0027305 | Stanwell Park Part A Downside 54.863 km to 55.735 km | Keith Holden | Bhaumik Trivedi | Options Assessment | Behind schedule | 2018 | 2020 | GHD addressed ST comments and issued REV0 Concept Options Report on 12-Feb-19 | Awaiting ST comments to FINAL (REV0) Concept Options Report and Acceptance of preferred stabilisation option - Gilken Gyro Pile
2126566 | 4200018767 | ST MSA MDP - Sydenham Track Drainage Redesign | Matt Presswell | Sam Widjaja | AFC | On track | TBA - pending response from ST on last deliverables | TBA - pending response from ST on last deliverables | AFC design delivered - scope complete Draft Pumping Design delivered - waiting ST approval to produce Final | Draft Pumping Design delivered - waiting ST approval to produce Final
2126603 |  | Clyde Eng and Maint Hub 11 kV Reticulation | Sudesh Nair
2126612 | P.0028099 / ED9872 | ST MSA MDP - Lithgow Track Drainage - ED9872 | Matt Presswell | Geoff Wooden | Concept Design | Behind schedule | 2017-10-13 | TBA | Draft Concept Design delivered, awaiting ST response | Final Concept Design
2126614 |  | Sydney Trains Woy Woy Supplementary Investigation | Henry Luo | Paul Mitiga |  |  |  |  | Awaiting last invoice $900. | Finalise job.
2126623 | ED9695 | ST Panel: Lewisham Substation Renewal | Ian Charlier | Soumava Dey | Detailed Design | Behind schedule | 28 Jun'19 | TBA by Sydney Trains (Expect Sept'19) | Delay in Construction by ST. All GHD deliverables submitted on-time and accepted per contract schedule. Sydney Trains advised that Construction would not be completed in FY18/19 as planned. GHD Still awaiting Sydney Trains to complete construction activities to allow GHD to finalise "As-Built" drawings and close-off job. | GHD to obtain Construction progress update from Sydney Trains. GHD to update drawings to "As-Built" once Redline mark-up's are received from Sydney Trains. Once actioned the job can be closed-off.
2127162 | 4200038278 | Wollstonecraft Station - Platforms Detailed Design | Daniel Byrne | Bhupen Khatri chhetri | Detailed Design | On track |  | End August | Adressing final commnets and completing additional variation investigations. | Finalise
2127278 | P.0027950 | OHW Staging - Lawson Stn Underpass Upgrade | Nobu Ito | Iqbal Dhal | AFC | On track | 01-07-2019 | 01-07-2019 | AFC submitted | Project Closure
2127484 | 4200058823 | EAB - Marayong Station, Pac Hwy OLB, Kuring-gai SH | Martyn Costello | Prakash Krishnappa | Construction Support | Behind schedule | No date set, as each of the three sites involved planned for construction work | Unknown, dependent on ST construction timing | First site in construction phase. Second site AFC has been accepted but site works not required. Final site AFC has been submitted in accordance with review comments, waiting on approval from ST. | Marayong - Complete Construction phase. Mt Kuring-Gai - No construction required. Pac Hwy OLBs - Confirm AFC submission ok
2127560 | P.0030227 | Edgecliff City on ESR (Replacement of Compressor) | Andrew Lim | Bhaumik Trivedi |  |  | 2019-08-26 | On hold, pending ST decision. | ST instructed GHD to put the project ON HOLD,as client want to re-evaluate the value of the project | Pending ST decision.
2127578 | P.0030789 | ST - Lilyvale & Helensburgh Tunnel Invest & Repair | Gordon Zuboski | Bhaumik Trivedi | Concept Design | On track
2127633 | P.0026550 | Figtree Creek Cleaning | Guillaume de Swardt | Sonia Gupta
2127638 | P.0029627 | Gosford Turntable Project | Andrew Lim | Kim Nael |  |  | No program, pending Phase 2 approval. | No program, pending Phase 2 approval. | Intial phase completed. Now pending client approval for the second phase of the project. | On hold. Pending variation approval.
2127648 | P.0026550 | ST MSA - East Richmond Bourke St. Level Crossing | Guillaume de Swardt | Sonia Gupta
2127653 |  | Sydney Trains Small Projects | Trent Stokes
2127727 | P.0027482 | ST - Canley Vale, Orphans Creek UB Refurbish | Gordon Zuboski | Geoff Wooden
2127728 | P.0028201 | ST - Emu Plains, Lapstone Creek UB - Refurbish | Gordon Zuboski | Geoff Wooden
2127729 | P.0027530 | ST - Holsworthy, Heathcote RD OB - Refurbish | Gordon Zuboski | Geoff Wooden
2127743 | P.0029881 | St Peters Padmount Substation Replacement | Drew Benesh | Prineesh Alphonse | Detailed Design | Behind schedule | 24-05-2019 | 06-09-2019 | Detailed design submitted for review. | 1. Detaield design meeting/presentation 2. Environmental and heritage investigations
2127749 | P.0030709 | Culvert Refurb Wyong 101.547km | Daniel Ghashghaie | Sam Widjaja
2127791 |  | Sydney Trains - PA Sidings | Alison Irons | [5 empty] | Project feasibility with ST for decision on how the project proceeds. | Await further ST instruction.
2127889 | P.0030295 | Hurstville Station Platform 4 Wall Stabilisation | Mike Leung | Paul Padman
2127903 | P.0034429 Purchase order: 4200086682 | Woy Woy Tunnel Remedial Options | Sami Ali Khan | Bhaumik Trivedi | Options Assessment | On track | Programme to be updated, pending approval of site works | Programme to be updated, pending approval of site works | Condition Assessment Report being finalised. Work beginning on Concept Options Report. | Sydney Trains to confirm approval of site works. GHD to finalise and submit Condition Assessment Report.
2127928 |  | Mount Victoria Remodelling REF | Karen Yale
2127943 | P.0029921 | Sydney Trains - Oakey Park SS Geotech | Clifton Thompson | Kin Phua
2127968 | P.0034249 | ST MSA MDP - Wyee Culvert Upgrade | Matt Presswell | Geoff Wooden | Options Assessment | On track | 2019-10-15 | 2019-10-15 | 70% Concept Design and Hydrology Study underway | Delivery of 70% Concept Design and Hydrology Study
2127971 | P.0029985 | St Leonards Station OHW E&B Upgrade | Nobu Ito | David Lee | AFC | On track | 01-07-2019 | 01-07-2019 | AFC submitted | Project Closure
2127982 | P.0030964 Purchase order: 4200080124 | Lavender Bay Stage 2&3 OHWS Investigation | Sami Ali Khan | Mathi Kaneshan | Preliminary Investigation | On track | Completed, pending Sydney Trains acceptance of final report. | Completed, pending Sydney Trains acceptance of final report. | Submitted final report | Sydney Trains to confirm acceptance of final report.
2127994 | 4200091853 | Emergency Exit Lighting Upgrade | Aamod Koirala
2127996 | P.0035101 | Strathfield Compressor House | Joel Schmidt | Bhaumik Trivedi
2127998 | P.0035025 | Berowra Station - Sewer Upgrade | Aamod Koirala | Fei Du |  | On track | 0
2128055 | P.4200094922 | ST Boronia Tunnel 1 & 2 Remediation | Gordon Zuboski | Bhaumik Trivedi | Condition Assessment | On track | 01-02-2019 | 01-02-2019 | Condition assessment reports (Draft A) submitted | awaiting Draft Condition assessment report comments
2128071 | 4200094667 | Tamworth Station - Post and Panel Inv, Des and Doc | Daniel Byrne | Asim Khan | Preliminary Investigation | Behind schedule |  | Mid October | Awaiting license agreement from JHR and TfNSW so the site investigation can go ahead. This process has been going since March and has had a major impact on the programme. This is regulalry discussed with Asim and is understood this is a situation that was unforeseen and nothing we can control. | Site visit
2128084 | PO 4200098055 | Lithgow Station SRA & Concept Design | Jason Hellmuth | Prineesh Alphonse | Concept Design | On track | Program being updated to allow for SoHI and revised concept design | 2019-08-30 | Activating provisional SoHI item to inform concept options, and revising concept options report | SoHI assessment by subconsultant
2128118 |  | Townhall Station QVB water leak investigation | Stuart Milling
2128132 |  | PSI, surface soil investigation, HMS, Tempe | Henry Luo | Paul Mitiga |  |  |  |  | Issue of report on hold, as requested by client. | Await ST.
2128144 |  | Harley Hill Road, Berry Level Crossing Automation | Stuart Healy | Sonia Gupta | Detailed Design | Behind schedule
2128267 | PO 4200109222 | Geotechnical Inspections - Lapstone and Zig Zag | Jason Hellmuth | Serge Kornev | Condition Assessment | On track | 2022-07-01 | 2022-07-01 | Providing marked-up 3D models to client, preparing for ad-hoc support (CPS) services and second round of inspections | Scoping walkover with Major Works / submission of 3D model
2128269 | PO 4200111004 | Glenbrook Overhang Remedial Design | Jason Hellmuth | Wael Fakih | Detailed Design | Behind schedule | 2019-08-12 | 2019-08-26 | Providing detailed design of steel strut solution, and also providing 3D model with Virtual Reality capacity for stakeholder engagement | 70% Detailed Design submission
2128272 |  | Lidcombe Station - Train Crew Toilet Refurbishment | Tejash Contractor
2128274 |  | Campbelltown Light Poles | Will Rickards | Preliminary Investigation | Preliminary Investigation
2128291 | P.0027573 / 4200107107 | MSA MDP - Casula Culvert Upgrade | Matt Presswell | Bhaumik Trivedi | Preliminary Investigation | At risk of being delayed | TBA - project started later than scoped, investigation findings are defining next steps | TBA - project started later than scoped, investigation findings are defining next steps | Survey and CCTV investigations are being reviewed to guide next steps | Clarify next steps and what additional investigations are required to be able to undertake the hydrology assessment
2128309 | P.0030301 | Katoomba Station Design Review | Mike Leung | Paul Padman
2128311 | 6000015107 | City Circle - OHW Options Study & Concept Design | Nobu Ito | Shabbir Hussain | Options Assessment | On track | 01-11-2019 | 01-11-2019 | Options Study Submission | Design Workshop then Concept design
2128322 | P.4200049803 | ST Underbridge Protection Project | Gordon Zuboski | Geoff Wooden | Concept Design | On track | 01-10-2018 | 15-08-2019 | Final Report Delevarable has been submitted | awaiting adiditonal comments (if applicable) or project to be finialised and remaining amount invoiced
2128323 | Purchase order: 4200109228 | Woy Woy 11kV Poles - Geotechnical Investigation | Sami Ali Khan | Prakash Krishnappa | Preliminary Investigation | On track | 2019-07-31 | 2019-07-31 | Submitted final report | Sydney Trains to confirm acceptance of final report.
2128329 | P.0028747 | Drainage at Wahroonga | Guillaume de Swardt | Sam Widjaja
2128333 | P.0039210 | Springwood Station Platform Wall Stabilisation | Ian Carvalho Campos | Paul Padman |  |  |  | Dependant on ST, see status | Waiting on ST comments on draft report | Response to comments
2128367 | 4200112173 | Wooloware Up Cutting Stabilisation | Sophie Liu | Prineesh Alphonse | Concept Design | On track | 18-Oct-19 Concept Design TBC Detailed Design | 18-Oct-19 Concept Design TBC Detailed Design | Preparing 70% concept design | -
2128388 | P.0030964 | Pile Toe Observations - Lavender Bay | James Scognamiglio | Mathi Kaneshan | Construction Support | On track | Est. 09/08/2019 | Est. 09/08/2019 | 1 of 2 weekends of pile supervision completed. | Final weekend of pile supervision to be undertaken during WE5 and report distributed during the week after
2128396 | P.0030744 | Wondabyne Culvert CPS - Construction | Daniel Ghashghaie | Sam Widjaja
2128412 |  | MSA MDP - Wondabyne Drainage and Culvert | Tom Patterson
2128421 | 4200112135 | MMC (Mortdale Maintenance Centre) Platform Upgrade | Daniel Byrne | Abdul Durrani | Preliminary Investigation | On track |  | Mid October | Awaiting confirmation of PO and agreed weekend for site visit to Mortdale MC. | Site visit
2220013 | P.0030710 | Sydney Trains - Dora Creek Culvert Extension | Brenton Secomb | Sam Widjaja | Detailed Design | On track |  | 1.5646e+18 | Draft Report issued. | Awaiting comments from ST Trains.
2220070 | P.0036856 | Rawson Road Level Crosisng Upgrade | Michael Monroe | Sonia Gupta | Concept Design | On track | 31-08-2019 | 31-08-2019 | Awaiting RFI information from Sydney Trains to finalise reports. | Once RFI received fro ST, report to be fialised and delivered to ST.
2316313 |  | Coniston Station Buildings - Structural Assessment | Stuart Milling
2316424 | 4200061824 | Mulgrave Station Sewer Connection | Adam Hunt | Kim Nael
2316486 |  | Sydney Trains - EDC Speaker Brackets | Ardalan Esfandiari
2316528 | 4200077499 | Carlton Station - Carpark Upgrade (Down-Side) | Peter Jameson | Asim Khan (not ESI) | Construction Support | On track |  |  | Completed | Invoice and close
2316610 | 4200086334 | Kogarah Station - Roof Leakage Investigations | Peter Jameson | Asim Khan (not ESI) | Detailed Design | On track | 01-10-2019 | 01-10-2019 | In Progress | Report writing
2316679 |  | Central Station Water Leak Investigation | Will Rickards | Preliminary Investigation | Preliminary Investigation
2316680 |  | Edgecliff Station - Review of Signage Anchor Bolts | Ardalan Esfandiari
4010220 |  | Sydney Trains - Blue Mountains Asbestos Removal | Oliver Hoschke
4010231 |  | Wombarra Ballast Remediation | David Coelli
12510265 |  | Clyde Stores Office Fitout | Elena Bullo | PROPOSAL
12510388 |  | MSA MDP - Oaky Park Sewer Rectification | Tom Patterson
12510395 |  | REF for G2B cabling project | Lisa King | PROPOSAL
12510401 |  | Campbelltown Re-signalling | Stuart Healy
12510429 |  | Bellambi Level Crossing Upgrade | Stuart Healy | Sonia Gupta | Preliminary Investigation | On track
12510685 |  | Retaining Wall Lavender Bay | Elizabeth Barraclough | PROPOSAL
12510799 |  | FMC Lighting System - Earthing and Bonding Design | Martyn Costello | PROPOSAL
210921436 |  | George St UB BR Refurbishment at Windsor | Luke Weatherstone | PROPOSAL
210921479 |  | St Leonard, Thornleigh and Woy Woy Frames Renewal | Michael Hastings | PROPOSAL
210921487 |  | P.0034894 MSA Condition Monitoring EAB | Martyn Costello | PROPOSAL
210921505 |  | Review of Civil Documents | Luke Weatherstone | PROPOSAL
210921544 |  | ST - East Hills Points Renewal | Michael Hastings | PROPOSAL
210921545 |  | ST - Awaba Points Renewals | Michael Hastings | PROPOSAL
210921566 |  | MSA MDP - Oakey Park Sewer Rectification | Tom Patterson
210921575 |  | Blacktown: Permanent Lighting | Trevor McMaster | PROPOSAL
210921586 |  | Penrith Re-signalling - Requirements Definition | Stuart Healy | PROPOSAL
210921605 |  | Peach Tree Creek Bridge Refurbishment | Ardalan Esfandiari | PROPOSAL
210921633 |  | Sydney Trains - Mt Druitt Section Hut ULX | Daniel Kamphorst | PROPOSAL
212655804 | P.0027305 | Stanwell Park Part B Downside 56.872 km to 57.045 km | Keith Holden | Bhaumik Trivedi | Options Assessment | Behind schedule | 2018 | 2020 | GHD addressed ST comments and issued REV0 Concept Options Report on 27-Mar-19 | Require additional investigations to proceed to detailed design. GHD negotiating with ST regarding REF and SoHi scope and price
230909003 |  | Flemington Car Sheds - Track Reconstruction | Michael Hastings | PROPOSAL
230909056 |  | ST - Omega Tunnels Track Reconstruction | Michael Hastings | PROPOSAL
21265570100 | P.0027306 | Coalcliff Embankment Downside 58.450km to 58.750km | Keith Holden | Bhaumik Trivedi | Detailed Design | Behind schedule | 2018 | 2019-08-30 | GHD addressing 70% detailed design comments. | GHD to finalise design followin 95% ST comments